compbird

Advertising & Marketing Plan — Launch through Month 6

Prepared July 2026 · Budget ≤ $500/month · Phase 1: Virginia · Phase 2: National

Working doc — revise as channel data comes in. Companion research: docs/regional-accuracy-2026-07.md, docs/blacksburg-head-to-head-2026-07.md, docs/LAUNCH-CHECKLIST.md.

# 1. Executive summary

compbird sells appraisal-grade comparables and live market reports in seconds, at $20/month, in a category where the incumbent (Lone Wolf Cloud CMA) charges $35–99/month and requires MLS membership. Our data moat is statewide Virginia assessor parcels joined to live listings — which means the product works for people the incumbents lock out: appraisers, investors, and FSBO sellers, plus agents who want a faster second source.

The plan: spend the first 90 days winning Virginia, where our coverage is real (130 counties/cities, ~319K closed sales in the pool) and every marketing dollar hits someone the product actually works for. Run on organic engines that cost time, not money — programmatic local SEO, published accuracy research, community presence, and direct brokerage outreach — with a small paid-search test to price acquisition. Go national in Months 4–6 once (a) unit economics are proven and (b) data coverage extends beyond VA + DC.

The math that matters: at $20/month, one Pro subscriber pays back ~$500/month of marketing at 25 subscribers. Target: 25 Pro by end of Month 3, 100 by end of Month 6.

# 2. Positioning & proof points

## One-liner

“A bird's-eye view of what every home is really worth.” Instant, evidence-backed home values from public records + live listings — no MLS membership required.

## The three claims we lead with

- Speed: a full comp report in seconds, not the 30–60 minutes a manual CMA takes in MLS tools.

- Honesty: we publish our error rates. The regional accuracy study and Blacksburg head-to-head (median |APE| ~15.5% on the production pool) are marketing assets no competitor matches — nobody else in this category shows their work.

- Access: built on statewide assessor parcels + public-records sales, so it works without MLS credentials — and at $20/month it undercuts Cloud CMA's $35–99/month tiers.

## Positioning guardrails

- Every asset carries the disclosure: “Estimates are model-driven opinions of value — not appraisals.” (Already on hero, footer, studio, pricing, PDF — keep it on ads too.)

- Never claim MLS data or Realtor affiliation. Say “public records + live listings.”

- Accuracy claims must trace to the two published studies; no rounding up.

# 3. Target audiences & messaging

Primary: agents and appraisers. Secondary: investors and FSBO sellers — we ship content for all four and let engagement data pick winners. Virginia has roughly 35,000 Realtors (Virginia Realtors association members) plus non-member licensees — the primary pool is large enough that even 0.1% penetration hits the Month-3 goal.

| Segment | Pain today | Message | Hook / CTA |
| --- | --- | --- | --- |
| Agents | CMAs are slow to build; MLS tools are clunky; tech fees stack up | Walk into every listing appointment with evidence. Client-ready comp reports in seconds — $20/mo, less than one coffee run | Free instant estimate → “See the full evidence” |
| Appraisers | Pre-inspection research is manual; thin-market comps are hard to find | A second data source in seconds: public-records comps, market trends, and a defensible paper trail. Supplemental research — not a USPAP appraisal | Free estimate on a property they know → compare |
| Investors / flippers | Running comps on every candidate deal is the bottleneck | Run the numbers before you make the offer. Comp any VA address in seconds | Free estimate; Pro for the full comp slate |
| FSBO / homeowners | Zillow feels wrong; agents feel salesy | Price your home like a pro — see the actual sales your value rests on | Free estimate, no card required |

Appraiser compliance note: market compbird to appraisers as research/desktop support only. Never imply output satisfies USPAP. This framing is also our shield against the “not an appraisal” objection.

# 4. Competitive snapshot

| Competitor | Price | Strength | Our wedge |
| --- | --- | --- | --- |
| Lone Wolf Cloud CMA | $35–99/mo (often free via MLS deals) | MLS integrations, brand, presentation polish | Price, speed, no-MLS access, published accuracy. Where an MLS gives Cloud CMA away, sell the second-source + speed angle instead of price |
| Zillow / public AVMs | Free | Consumer brand gravity | We show the comps, the evidence, and let you edit them — an estimate you can defend to a client, not a black box |
| Manual MLS CMA | Included in dues | Authoritative data | 30–60 min vs seconds; ours is shareable as a clean PDF and works outside MLS coverage |

The estimated ~$100 cost-per-lead common in real-estate ad benchmarks is why we do NOT lead with paid: at $20/month, paid CAC only works if annual retention is strong. Paid is a measurement tool in Phase 1, not a growth engine.

# 5. Phase 1 — Virginia (Months 1–3)

## 5.1 Product-led loop (free, highest priority)

- Free estimate as the ad. “No card required” instant estimates are the top of every funnel below. Every CTA in every channel points at it.

- Watermarked free PDFs are distribution. Free-tier reports circulate inside offices and among clients carrying the compbird mark; Pro removes it. Make the watermark include the URL.

- Referral offer: give-a-month/get-a-month for Pro referrals. Cheap to build, and agents talk to agents all day.

## 5.2 Programmatic local SEO (free, compounding)

- Publish a market-report landing page per covered county/city (~130 pages: “Fairfax County home values & market report”), fed by the same engine data as the in-app market panel. This is the plan's biggest lever: local-intent searches with thin competition outside the Zillow tier.

- Publish the two accuracy studies as web pages (“How accurate is compbird? We tested it on 20 real sales”). Transparency content earns links and disarms skeptics.

- Basic hygiene is already shipped (robots, sitemap, OG images) — add per-page metadata and internal links from report pages to the estimate CTA.

## 5.3 Direct outreach & demos (free, founder time)

- Email/LinkedIn 10 managing brokers per week in NoVA, Richmond, Virginia Beach, Roanoke/Blacksburg offering a 15-minute office demo (“lunch and learn”). One office of 30 agents beats a month of ads.

- Offer local Realtor associations (NVAR, Richmond AR, etc.) a free member webinar on pricing in the current market — teach first, demo second.

- For appraisers: reach out through Virginia appraiser groups and forums with the supplemental-research framing.

## 5.4 Community presence (free, steady drip)

- Be useful (not promotional) in r/realtors, r/RealEstate, r/appraisal, BiggerPockets forums, and Virginia agent Facebook groups. Answer pricing questions; link the free estimate when directly relevant.

- Post one comp-of-the-week breakdown on LinkedIn + a short video walkthrough (screen recording is enough) showing an address → report in 30 seconds.

- Collect and publish testimonials from the first 10 Pro users; add to landing + pricing pages.

## 5.5 Paid search test (the ~$250/mo)

- Google Search only, geo-fenced to Virginia, exact/phrase match on high-intent terms: “cma software,” “comp software real estate,” “how to price a listing,” “home value report for sellers,” “comps for my house.” Real-estate CPCs run ~$2–5, so $250 ≈ 60–110 clicks/month — enough to read signal by Month 3, not enough to scale.

- Send clicks to a dedicated landing page with the free-estimate CTA; tag everything (UTM) from day one.

- Kill rule: any ad group with a free-signup cost above $15 after ~$150 spend gets paused; measured free→Pro conversion sets the real ceiling later.

## 5.6 Event: Virginia Realtors 2026 Convention

- September 15–17, 2026, Williamsburg Lodge. Attend as a member of the crowd, not an exhibitor (booths blow the budget): registration + hallway demos on a laptop + a pocket of QR cards to the free estimate.

- Goal: 50 scanned signups and 5 office-demo commitments. If Phase 1 is going well, evaluate an NVAR convention presence later in the fall.

# 6. Budget — ≤ $500/month

| Line item | Monthly | Notes |
| --- | --- | --- |
| Google Search test (VA geo-fence) | $250 | Months 2–3 (Month 1: $0 — funnel + tracking first) |
| Boost / retargeting (Meta or LinkedIn) | $75 | Retarget site visitors + boost the best organic post |
| Tools (video, design, scheduling) | $50 | Free tiers first: Canva, Buffer, OBS; upgrade only when blocked |
| QR cards, misc. print | $25 | Convention + office demos |
| Flex / experiments | $100 | Newsletter sponsorship in a VA agent newsletter, contest, or roll into ads |
| Total | $500 | Month 1 actual spend ≈ $150; underspend rolls to the convention month |

One-time (outside monthly): Virginia Realtors Convention registration + travel (budget from the flex line across Months 1–3, roughly $300–500 total). Skip the booth this year.

# 7. 90-day calendar (July → September 2026)

| Month | Ship / do | Success looks like |
| --- | --- | --- |
| July (M1) | Finish launch checklist blockers (Stripe, domain, email, legal). Analytics + UTM tracking. Publish accuracy studies as pages. First 20 county SEO pages. Socials live. Start broker outreach (10/wk). Register for VA Realtors Convention | Site live; 50 free accounts (friends, outreach, communities); 3 office demos booked; tracking trustworthy |
| August (M2) | Remaining SEO pages. Start $250 Google test + retargeting. Referral program live. Weekly LinkedIn comp breakdown + video. First testimonials on site. Webinar pitch to local associations | 150 total free accounts; 10 Pro ($200 MRR); ad CAC data; 1 webinar scheduled; SEO pages indexing |
| September (M3) | VA Realtors Convention (Sept 15–17). Double down on whichever channel drove Pros; kill what didn't. Publish “what 90 days of real usage taught us” post. Decide Phase 2 scope from coverage + funnel data | 300 total free accounts; 25 Pro ($500 MRR — marketing breakeven); 50 convention signups; free→Pro ≥ 6% |

# 8. Phase 2 — National (Months 4–6)

Gate, not date: national marketing waits on two proofs — (1) free→Pro conversion ≥ ~6% with CAC under ~$60 in Virginia, and (2) data coverage beyond VA + DC (the current supplemental pool is 95.6% Virginia). Marketing nationally before coverage exists manufactures churn and bad reviews. If coverage expands state-by-state, repeat the Virginia playbook per state — it's designed to be cloned.

- Scale what won: raise paid budget only on ad groups with proven Pro-payback; expand SEO pages to every newly covered county.

- Partnerships: affiliate/rev-share with real-estate YouTubers, podcasters, and coaches (investor + new-agent niches convert on tools); team/brokerage plans as a sales motion once 5+ offices ask.

- Marketplaces & directories: list on software directories (G2, Capterra) and real-estate tool roundups; pitch the accuracy-transparency angle to trade press (Inman, HousingWire) — “the CMA tool that publishes its error rate” is a story.

- National events: evaluate one national conference (NAR NXT or an appraiser summit) only after $5K+ MRR.

# 9. Metrics & targets

| Metric | Month 3 | Month 6 | Notes |
| --- | --- | --- | --- |
| Free accounts (cumulative) | 300 | 1,200 | Any channel; UTM-tagged |
| Activation (ran ≥1 report) | 70% | 80% | Onboarding already shipped; watch drop-off |
| Free → Pro conversion | 6% | 8% | The number that decides Phase 2 |
| Pro subscribers / MRR | 25 / $500 | 100 / $2,000 | 25 Pro = marketing breakeven |
| Blended CAC | ≤ $60 | ≤ $60 | 3-month payback at $20/mo |
| Monthly churn | < 8% | < 5% | Exit survey on cancel from day one |
| SEO pages indexed / organic visits | 100 / 500 mo. | 130+ / 3,000 mo. | Search Console |

Review weekly (30 min): signups by source, conversions, one decision per week about what to stop, start, or double.

# 10. Risks & watch-outs

- Regulatory/claims risk: ad copy repeating the “not an appraisal” disclosure is non-negotiable; attorney review of terms/privacy is already on the launch checklist — add ad copy to that review.

- MLS/association friction: some associations view non-MLS valuation tools warily. The webinar/teaching posture and public-records framing keep us welcome; never scrape or imply MLS sourcing.

- Accuracy backlash: a public miss on a specific home is inevitable. The published error-rate studies are the pre-built response — we said ~15% median error out loud, on purpose.

- Founder-time as the real budget: this plan costs ~10–15 hrs/week. If that's not available, cut community drip before cutting broker outreach and SEO — those two compound.

- Cloud CMA price response: if the incumbent discounts, our moat is speed + no-MLS access + transparency, not the $15 gap. Don't get dragged into a price war.

# Appendix — sources & assumptions

- Virginia Realtors membership ~34,000–38,000 (virginiarealtors.org; association LinkedIn). Licensed-agent total is larger (DPOR).

- Cloud CMA pricing $35/mo standalone, $49 CMA+Homebeat, $99 suite; frequently free via MLS partnerships (lwolf.com; Capterra/GetApp 2026 listings).

- Real-estate Google Ads CPC ~$2–5, CPL often ~$100 (2026 industry benchmark roundups — directional, not gospel).

- Virginia Realtors 2026 Annual Convention: Sept 15–17, Williamsburg Lodge (virginiarealtors.org / nar.realtor event listings).

- Product facts (pricing, coverage, accuracy, paywall) from this repo: landing copy, docs/regional-accuracy-2026-07.md, docs/blacksburg-head-to-head-2026-07.md, docs/LAUNCH-CHECKLIST.md.